## Project Tracker
ID | Week | Module | Task | Importance | Deliverable | Status
T001 | Week 1 | Setup | Create Project Structure | High | Folder Structure | Completed
T002 | Week 1 | Setup | Create GitHub Repository | High | Public Repository | Completed
T003 | Week 1 | Setup | Install Python | High | Working Python | Completed
T004 | Week 1 | Setup | Install PostgreSQL | High | Working Database | Completed
T005 | Week 1 | Setup | Cricket Domain Research | High | cricket_domain_notes.md | Completed
T006 | Week 1 | Setup | KPI Definition | High | project_kpis.md | Completed
T007 | Week 1 | Setup | Create Tracker | Medium | Tracker Sheet | Completed
T008 | Week 1 | Setup | System Architecture Diagram | High | system_architecture.md | Completed
T009 | Week 1 | Biomechanics | Batting Biomechanics Research | High | batting_biomechanics.md | Completed
T010 | Week 1 | Biomechanics | Shot Phases Analysis | High | Shot Phase Notes | Completed
T011 | Week 1 | Biomechanics | Head Stability Research | High | Head Stability Notes | Completed
T012 | Week 1 | Biomechanics | Balance Analysis | High | Balance Notes | Completed
T013 | Week 1 | Biomechanics | Bat Speed Research | High | Bat Speed Notes | Completed
T014 | Week 1 | Biomechanics | Follow Through Analysis | High | Follow Through Notes | Completed
T015 | Week 1 | Biomechanics | Shot Selection Framework | High | Shot Analysis Table | Completed
T016 | Week 1 | Analytics Design | Analytics Mapping Framework | High | Mapping Tables | Completed
T017 | Week 2 | Sensor Module | ESP32 Setup | High | Working ESP32 | Pending
T018 | Week 2 | Sensor Module | MPU6050 Integration | High | Sensor Readings | Pending
T019 | Week 2 | Sensor Module | Save Sensor Data to CSV | High | Sensor Dataset | Pending
T020 | Week 3 | Dataset Collection | Video Collection | High | Shot Videos | Pending
T021 | Week 3 | Dataset Collection | Shot Labeling | High | Labeled Dataset | Pending
T022 | Week 3 | Feature Engineering | Feature Blueprint | High | Feature List | Pending
T023 | Week 4 | Vision Module | MediaPipe Setup | High | Pose Detection | Pending
T024 | Week 4 | Vision Module | Landmark Extraction | High | Landmark CSV | Pending
T025 | Week 5 | ML Models | Train Baseline Model | High | Random Forest Model | Pending
T026 | Week 5 | ML Models | Train XGBoost Model | High | Final Model | Pending
T027 | Week 6 | Analytics Engine | Timing Score Engine | High | Timing Metric | Pending
T028 | Week 6 | Analytics Engine | Power Score Engine | High | Power Metric | Pending
T029 | Week 7 | Dashboard | Build Streamlit Dashboard | High | Dashboard | Pending
T030 | Week 8 | Strategy Engine | Win Probability Model | High | ML Model | Pending
T031 | Week 8 | Portfolio | Final Report and Demo | High | Report + Video | Pending